## Bugs
Bug ID | Title | Module | Team | Priority | Type | Environment | Browser / Device | Steps to Reproduce | Expected Result | Actual Result | Test Case ID | Assigned To | Reported By | Reported On | Status | Root Cause | Notes
BUG-001 | Duplicate "Generated_" prefix on downloaded file names | MSA GENERATION |  | P3 | Functional |  |  | Generate an MSA document and download the PDF/Word output. | Downloaded file is named with a single prefix, e.g. "MSA_<company>.pdf". | File downloaded as "Generated_Generated_MSA.pdf" with the prefix duplicated. | TC-MSA-001 | Pavan Nikhil | Prem Kommi | 6/17/2026 | Fixed | generatedBaseName was set to 'Generated_MSA' while the download template also prepended "Generated_". | Fix: baseName changed to 'MSA'; download template no longer double-prepends "Generated_". (script.js, commit 921a432)
BUG-002 | City/state/ZIP silently dropped from extracted address | EXTRACTION |  | P1 | Functional |  |  | Extract a W-9 where the "City, state, and ZIP code" label does not OCR cleanly. | Both street address and city/state/ZIP are populated. | City/state/ZIP silently dropped, leaving the address incomplete. | TC-EXT-003 | Pavan Nikhil | Prem Kommi | 6/17/2026 | Fixed | Street and city/state/ZIP were captured via two independent regex passes, each dependent on the line-6 label extracting cleanly. | Fix: lines 5+6 now captured as one block; label position marked before whitespace-collapsing, then split on that marker with fallback heuristics. (script.js, commit 921a432)
BUG-003 | "Requester" address header truncates applicant's own street address | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 where "Requester's name and address" is printed beside line 5. | Applicant's own street address is captured in full. | Street address capture was cut off prematurely at the word "Requester". | TC-EXT-004 | Pavan Nikhil | Prem Kommi | 6/17/2026 | Fixed | "Requester" was included in the NEXT_LABEL_PHRASES stop-label list. | Fix: "Requester" removed from stop labels; the header text is now explicitly stripped from the captured block instead. (script.js, commit 921a432)
BUG-004 | Stored file/history names rendered via innerHTML (XSS) | SECURITY |  | P1 | Security |  |  | Upload a file, or create a history entry, whose filename contains HTML/script markup (e.g. an <img> tag with an onerror handler). | Filename is displayed as plain text; no script executes. | Filename markup was injected into the DOM and could execute arbitrary script. | TC-SEC-001 | Pavan Nikhil | Prem Kommi | 6/18/2026 | Fixed | renderFileList, setMsaTemplate, and renderHistory built list items via li.innerHTML = `<span>${file.name}</span>...` with no escaping. | Fix: switched to textContent assignment on separately created <span> elements. (script.js, commit 3bc7cad)
BUG-005 | Generated-document history leaks across browser tabs/sessions | HISTORY |  | P1 | Security |  |  | Generate a document in one tab (with real SSN/EIN data filled in), then open History in a different or new tab, or after closing the original tab. | Each tab/session sees only its own generated-document history. | Any tab could read another (even closed) tab's generated documents indefinitely. | TC-HIST-001 | Pavan Nikhil | Prem Kommi | 6/18/2026 | Fixed | IndexedDB history entries had no session scoping and were never purged. | Fix: each tab gets a random per-tab session ID (sessionStorage); only matching entries are shown, stale entries purged on load. (script.js, commit 3bc7cad)
BUG-006 | Auth overlay bypassable via keyboard Tab navigation | AUTH |  | P0 | Security |  |  | Load the app signed out, then press Tab repeatedly (or Tab+Enter) to move focus past the sign-in overlay. | Keyboard focus cannot reach any app content until sign-in succeeds. | Tab+Enter could reach #navHistoryLink/#navGeneratorLink behind the overlay, exposing document history with no sign-in. | TC-AUTH-001 | Pavan Nikhil | Prem Kommi | 6/19/2026 | Fixed | #authGate overlay only visually covered the app via z-index, which has no effect on focus/tab order. | Fix: added inert attribute to introOverlay, .topnav, #mainStage, #historyView; removed only after successful sign-in. (index.html, auth-ui.js, commit 1718f3a)
BUG-007 | Domain allow-list enforced only client-side | AUTH |  | P1 | Security |  |  | Inspect/modify the isAllowedEmail check via browser devtools during sign-in with a non-allowed account. | Account authorization is enforced server-side and cannot be bypassed from the client. | Allow-list logic ran entirely in shipped browser JS, inspectable and tamperable. | TC-AUTH-002 | Pavan Nikhil | Prem Kommi | 6/19/2026 | Fixed | isAllowedEmail's domain check had no server-side enforcement behind it. | Fix: removed client-side allow-list; authorization now enforced by Entra's "Assignment required" setting, with AccessDeniedError handling Entra's own redirect-back error. (auth.js, authConfig.js, commit 1718f3a)
BUG-008 | Extraction failure hides the manual-entry fields it tells the user to use | EXTRACTION |  | P0 | Functional |  |  | Upload a W-9 that fails OCR/parsing (e.g. an unreadable scan). | Manual-entry field panel is shown so the user can fill fields by hand as instructed. | Status message told the user to "fill fields manually", but the field panel stayed hidden. | TC-EXT-005 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | The failure path never called renderW9Summary(). | Fix: added revealManualW9Entry() to force-render the summary panel and validation status on every failure path. (script.js, commit bc7ad01)
BUG-009 | Tax ID Type dropdown leaves stale/mismatched number on screen | EXTRACTION |  | P1 | Functional |  |  | Extract a W-9 with both SSN and EIN candidates found, then switch the Tax ID Type dropdown (e.g. SSN -> EIN). | Displayed Tax ID number updates to match the newly selected type. | Dropdown updated the type label but left the previously displayed/stored number showing in the old format. | TC-EXT-006 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | The change handler updated selected_tax_id_type but never updated the displayed/stored number. | Fix: new handler swaps in the correct stored ssn/ein value for the newly selected type. (script.js, commit bc7ad01)
BUG-010 | Re-uploading a W-9 accumulates old files and stale data | EXTRACTION |  | P1 | Functional |  |  | Upload a W-9, then upload a second, different W-9 without removing the first. | File list and extracted fields reflect only the newly uploaded document. | Old files accumulated in the list and stale extracted data/summary could persist from the prior upload. | TC-EXT-007 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | uploadedFiles.concat(...) kept prior files; extraction state/panels were never reset on new upload. | Fix: addFiles now replaces the file list and resets extraction state/panels on every upload. (script.js, commit bc7ad01)
BUG-011 | Blank TIN boxes OCR as false-positive digits | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 where the SSN or EIN box is left blank (only the printed border/cell-divider lines are present). | Tax ID field is left empty, not populated with fabricated digits. | Printed border/cell-divider lines were misread as digits on an empty box. | TC-EXT-013 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | No ink-density check was performed before trusting a digit reading. | Fix: added regionInkDensity/MIN_DIGIT_INK_DENSITY gate requiring real ink before accepting a digit reading. (script.js, commit bc7ad01)
BUG-012 | Address parser truncates street text before a multi-digit suite number | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 with a multi-digit suite number immediately before the city (e.g. "Suite 240, Springfield"). | Full "Suite 240" is retained in the street address. | Regex consumed the last digit of "Suite 240" right before the city label, truncating the suite number. | TC-EXT-018 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | Bare single-digit match with no boundary check. | Fix: added negative lookbehind (?<!\d) so it only matches genuinely standalone digits. (script.js, commit bc7ad01)
BUG-013 | Address parser fabricates a fake city name from OCR noise | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 scan with OCR noise producing a stray all-caps token near the address (e.g. scan artifact "CR"). | Only genuine Title Case city names are captured. | All-caps noise tokens could chain into a fabricated fake city name. | TC-EXT-019 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | [A-Z][A-Za-z'.-]* pattern allowed an all-caps noise token to match as a valid city. | Fix: now requires a lowercase letter after the capital, enforcing genuine Title Case. (script.js, commit bc7ad01)
BUG-014 | MSA generation errors shown in the wrong panel | MSA GENERATION |  | P2 | UI |  |  | Trigger an error during MSA document generation (e.g. an invalid template). | Error message appears in the (opened) preview panel it describes. | Error appeared in the unrelated left status line while the preview panel stayed closed. | TC-MSA-003 | Pavan Nikhil | Prem Kommi | 6/25/2026 | Fixed | setStatus wrote generation errors to the general status line instead of the preview panel. | Fix: added setPreviewStatus(), which force-opens the preview panel on error. (script.js, commit bc7ad01)
BUG-015 | Auto-detected Tax ID Type overrides manual dropdown selection | EXTRACTION |  | P2 | Functional |  |  | Manually select a Tax ID Type from the dropdown, then continue typing digits into the Tax ID field. | Manually selected type stays fixed; it changes only via explicit dropdown selection. | Typing digits could auto-flip the dropdown based on dash position, overriding the user's manual choice. | TC-EXT-020 | Pavan Nikhil | Prem Kommi | 8/26/2026 | Fixed | detectTaxIdType() ran on every keystroke and reassigned the type. | Fix: removed auto-detection; type now changes only via explicit dropdown selection. (script.js, uncommitted)
BUG-016 | Manual-field validation errors reuse the wrong status line | UI |  | P3 | UI |  |  | Enter invalid data into a manual field, then correct it. | Validation error clears automatically once the field is corrected. | Validation error shared the general status line and did not auto-clear after correction. | TC-UI-003 | Pavan Nikhil | Prem Kommi | 8/26/2026 | Fixed | No dedicated status handler existed for manual-field validation. | Fix: added setManualFieldsStatus(), which clears automatically. (script.js, uncommitted)
BUG-017 | "Generate New Document" button visible on the wrong wizard steps | UI |  | P2 | UI |  |  | Navigate the document wizard to a step where the "Generate New Document" button should not apply. | Button is hidden on steps where it does not apply. | Button stayed visible on the wrong wizard steps. | TC-UI-004 | Pavan Nikhil | Prem Kommi | 8/26/2026 | Fixed | A same-specificity .btn{display:inline-flex} CSS rule overrode the bare hidden attribute after the button moved to an always-rendered section. | Fix: added explicit .btn-new-doc[hidden]{display:none} override. (index.html, style.css, uncommitted)
ENH-018 | Blank TIN boxes OCR as false-positive digits | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 where the SSN or EIN box is left blank (only the printed border/cell-divider lines are present). | Tax ID field is left empty, not populated with fabricated digits. | Printed border/cell-divider lines were misread as digits on an empty box. | TC-EXT-013 |  |  | 6/25/2026 | Completed | No ink-density check was performed before trusting a digit reading. | Fix: added regionInkDensity/MIN_DIGIT_INK_DENSITY gate requiring real ink before accepting a digit reading. (script.js, commit bc7ad01)
ENH-019 | 10-digit OCR misreads not corrected safely | EXTRACTION |  | P1 | Functional |  |  | Extract a W-9 where OCR reads a 9-digit TIN as 10 digits, with the spurious digit not at the start. | The genuine 9-digit run is recovered correctly regardless of where the spurious digit lands. | Code blindly sliced off index 0, only correcting a leading spurious digit and mangling other cases. | TC-EXT-014 |  |  | 6/25/2026 | Completed | Fixed-position trim assumed the extra digit was always the first character. | Fix: extracts the longest contiguous digit run instead of blindly trimming a fixed position. (script.js, commit bc7ad01)
ENH-020 | Grid/box border lines fuse into digit glyphs | EXTRACTION |  | P1 | Functional |  |  | Extract a W-9 with a boxed TIN form where cell border strokes touch the printed digits. | Digits are read correctly despite adjacent border lines. | Tesseract dropped or misread digits whose border stroke fused into the glyph. | TC-EXT-015 |  |  | 6/25/2026 | Completed | No preprocessing removed border lines before OCR. | Fix: added whiteOutGridLines() to paint over border columns before OCR. (script.js, commit bc7ad01)
ENH-021 | Low-contrast photo scans of TIN boxes unreadable | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 photographed under poor lighting (low ink/paper contrast). | Digits/borders are still binarized and read correctly. | Low-contrast crops failed OCR binarization, resulting in missed or blank reads. | TC-EXT-016 |  |  | 6/25/2026 | Completed | No contrast normalization was applied to the crop before OCR. | Fix: added stretchContrast() to stretch crop luminance to full black/white. (script.js, commit bc7ad01)
ENH-022 | Single unconfirmed OCR reading of a TIN silently accepted | EXTRACTION |  | P1 | Functional |  |  | Extract a W-9 where the whiteout-preprocessed OCR pass misreads one digit differently than the raw pass (e.g. 6 vs 8), with only weak agreement. | Ambiguous/low-confidence readings are rejected rather than silently accepted. | A reading with only 2 agreeing votes was accepted despite being wrong. | TC-EXT-017 |  |  | 6/25/2026 | Completed | Confidence threshold (bestCount >= 2) was too low, with no distinction between whiteout-pass and raw-pass votes. | Fix: raised threshold to bestCount >= 3 with tie-detection between whiteout/raw vote groups. (script.js, commit bc7ad01)
ENH-023 | Address parser truncates street text before a multi-digit suite number | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 with a multi-digit suite number immediately before the city (e.g. "Suite 240, Springfield"). | Full "Suite 240" is retained in the street address. | Regex consumed the last digit of "Suite 240" right before the city label, truncating the suite number. | TC-EXT-018 |  |  | 6/25/2026 | Completed | Bare single-digit match with no boundary check. | Fix: added negative lookbehind (?<!\d) so it only matches genuinely standalone digits. (script.js, commit bc7ad01)
ENH-024 | Address parser fabricates a fake city name from OCR noise | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 scan with OCR noise producing a stray all-caps token near the address (e.g. scan artifact "CR"). | Only genuine Title Case city names are captured. | All-caps noise tokens could chain into a fabricated fake city name. | TC-EXT-019 |  |  | 6/25/2026 | Completed | [A-Z][A-Za-z'.-]* pattern allowed an all-caps noise token to match as a valid city. | Fix: now requires a lowercase letter after the capital, enforcing genuine Title Case. (script.js, commit bc7ad01)
ENH-025 | MSA generation errors shown in the wrong panel | MSA GENERATION |  | P2 | UI |  |  | Trigger an error during MSA document generation (e.g. an invalid template). | Error message appears in the (opened) preview panel it describes. | Error appeared in the unrelated left status line while the preview panel stayed closed. | TC-MSA-003 |  |  | 6/25/2026 | Completed | setStatus wrote generation errors to the general status line instead of the preview panel. | Fix: added setPreviewStatus(), which force-opens the preview panel on error. (script.js, commit bc7ad01)
ENH-026 | File upload rejects image scans despite bundled OCR support | UPLOAD |  | P2 | Functional |  |  | Attempt to upload a photo/scan of a W-9 (JPEG/PNG/HEIC) via the file picker. | Image files are accepted, since tesseract.js OCR is bundled to process them. | File picker/validation rejected image files, accepting only application/pdf. | TC-UPL-001 |  |  | 6/25/2026 | Completed | accept="application/pdf" attribute excluded image MIME types. | Fix: extended accept to include jpeg/png/webp/heic/heif. (index.html, commit bc7ad01)
ENH-027 | Extraction review warning easy to miss | UI |  | P2 | UI |  |  | Extract a W-9 and view the field-review screen. | A clearly visible warning tells the user to review automated extraction results. | Warning was plain, low-visibility hint text placed below the fields, easy to overlook. | TC-UI-001 |  |  | 6/25/2026 | Completed | No alert styling/role was applied to the warning text. | Fix: replaced with a role="alert" banner with icon, moved above the fields. (index.html, commit bc7ad01)
ENH-028 | Auto-detected Tax ID Type overrides manual dropdown selection | EXTRACTION |  | P2 | Functional |  |  | Manually select a Tax ID Type from the dropdown, then continue typing digits into the Tax ID field. | Manually selected type stays fixed; it changes only via explicit dropdown selection. | Typing digits could auto-flip the dropdown based on dash position, overriding the user's manual choice. | TC-EXT-020 |  |  | 8/26/2026 | Completed | detectTaxIdType() ran on every keystroke and reassigned the type. | Fix: removed auto-detection; type now changes only via explicit dropdown selection. (script.js, uncommitted)
ENH-029 | Tax ID field shows no dash formatting while typing | UI |  | P3 | UI |  |  | Type digits into the Tax ID field one at a time. | Dashes appear live as digits are typed (e.g. XX-XXXXXXX). | No formatting appeared until all 9 digits had been entered. | TC-UI-002 |  |  | 8/26/2026 | Completed | formatTaxId only formatted a complete 9-digit value. | Fix: added formatTaxIdPartial for live dash formatting on every keystroke. (script.js, uncommitted)
ENH-030 | Recoverable length+1 OCR TIN readings discarded | EXTRACTION |  | P2 | Functional |  |  | Extract a W-9 where OCR consistently reads one extra digit beyond the true 9-digit TIN, corroborated by another clean reading. | The extra digit is trimmed and the correct 9-digit value recovered. | Such readings were discarded entirely instead of being corrected. | TC-EXT-021 |  |  | 8/26/2026 | Completed | No mechanism existed to trim a corroborated length+1 reading. | Fix: added corroborated front/back trimming logic for length+1 readings. (script.js, uncommitted)
ENH-031 | Manual-field validation errors reuse the wrong status line | UI |  | P3 | UI |  |  | Enter invalid data into a manual field, then correct it. | Validation error clears automatically once the field is corrected. | Validation error shared the general status line and did not auto-clear after correction. | TC-UI-003 |  |  | 8/26/2026 | Completed | No dedicated status handler existed for manual-field validation. | Fix: added setManualFieldsStatus(), which clears automatically. (script.js, uncommitted)
ENH-032 | "Generate New Document" button visible on the wrong wizard steps | UI |  | P2 | UI |  |  | Navigate the document wizard to a step where the "Generate New Document" button should not apply. | Button is hidden on steps where it does not apply. | Button stayed visible on the wrong wizard steps. | TC-UI-004 |  |  | 8/26/2026 | Completed | A same-specificity .btn{display:inline-flex} CSS rule overrode the bare hidden attribute after the button moved to an always-rendered section. | Fix: added explicit .btn-new-doc[hidden]{display:none} override. (index.html, style.css, uncommitted)

## Enhancement
Enhancement ID | Title | Category | Module | Priority | Effort | What Changed | Why It Matters | Benefit Delivered | Technical Approach | Status | Delivered | Source
ENH-001 | Long business name/address truncated at 60 characters | Extraction Accuracy | EXTRACTION | P2 | S | cap raised to 160 characters. | Capture cut off at exactly 60 characters, dropping the remainder of longer values. | Long business names/addresses no longer get cut off in the generated MSA. | captureAfterLabel applied a hard Math.min(cutoff, 60) limit. -> cap raised to 160 characters. | Completed | 6/17/2026 | script.js, commit 921a432
ENH-002 | Inserted MSA field values render in bold | Document Fidelity | MSA GENERATION | P2 | S | now skips forward past any whitespace-only run remainder to land in the real | Inserted replacement text rendered bold, inheriting the label's run style. | Filled-in values render with correct document formatting instead of stray bold text. | replaceAfterLabelInParagraphs spliced the new value into the same Word run that held the label's trailing whitespace. -> now skips forward past any whitespace-only run remainder to land in the real | Completed | 6/17/2026 | non-bold) value run. (script.js, commit 921a432
ENH-003 | TIN label search anchors on instructional prose instead of the field label | Extraction Accuracy | EXTRACTION | P1 | M | search scoped to extractPartISection using bounded/last-match logic. | Label search matched the form's own explanatory sentence instead of the real label next to the box. | Fewer false-anchor mismatches on W-9s with dense Part I instructional text. | Whole-document substring search for the label text, not scoped to the actual field area. -> search scoped to extractPartISection using bounded/last-match logic. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-004 | Fixed-fraction crop regions miss shifted or rotated scans | Extraction Coverage | EXTRACTION | P1 | L | added dynamic full-page fuzzy label anchoring | Fixed-fraction crop regions missed the real label/value location entirely, returning nothing. | W-9 scans that are shifted, cropped, or rotated can now be extracted at all. | TIN_BOX_REGION / SSN_ROW_FRAC / EIN_ROW_FRAC were tuned to a single fixed layout. -> added dynamic full-page fuzzy label anchoring | Completed | 6/25/2026 | findTinCropRegion/findAddressCropRegion) with the fixed region kept only as fallback. (script.js, commit bc7ad01
ENH-005 | AcroForm field values appended at document end break label anchoring | Extraction Coverage | EXTRACTION | P1 | M | field values now spliced into text at their real y-position among page items. | Field values were concatenated to the end of the combined text, breaking label-anchored regex extraction. | Fillable-form (AcroForm) W-9 PDFs are now supported for direct field extraction. | extractAcroFormDirectFields appended all field values regardless of their original position on the page. -> field values now spliced into text at their real y-position among page items. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-006 | TIN digit row OCR drops a digit at the row edge | Extraction Accuracy | EXTRACTION | P1 | M | now OCRs both a widened-left and an as-detected crop and only trusts agreeing readings. | A digit at the edge of the row could be silently dropped with no cross-check. | Fewer dropped digits at the edge of a boxed TIN row on tightly-cropped scans. | Tesseract's line detection could clip the row edge with nothing to catch it. -> now OCRs both a widened-left and an as-detected crop and only trusts agreeing readings. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-007 | Capture still truncated at 160 chars even past a real stop label | Extraction Accuracy | EXTRACTION | P2 | S | now uses the unbounded real stop-label index, only capping at 220 chars when no stop label is found. | Value was still chopped off at 160 characters even though the matched stop label was further away. | Long values are no longer clipped once a genuine stop label is found further away. | Cutoff was computed as Math.min(matchedStopIndex, 160). -> now uses the unbounded real stop-label index, only capping at 220 chars when no stop label is found. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-008 | 10-digit OCR misreads not corrected safely | Extraction Accuracy | EXTRACTION | P1 | M | extracts the longest contiguous digit run instead of blindly trimming a fixed position. | Code blindly sliced off index 0, only correcting a leading spurious digit and mangling other cases. | 9-digit TIN recovered correctly even when the spurious 10th digit isn't at the start. | Fixed-position trim assumed the extra digit was always the first character. -> extracts the longest contiguous digit run instead of blindly trimming a fixed position. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-009 | Grid/box border lines fuse into digit glyphs | Extraction Accuracy | EXTRACTION | P1 | M | added whiteOutGridLines | Tesseract dropped or misread digits whose border stroke fused into the glyph. | Digits are no longer lost where a table border stroke touches the glyph. | No preprocessing removed border lines before OCR. -> added whiteOutGridLines | Completed | 6/25/2026 | ) to paint over border columns before OCR. (script.js, commit bc7ad01
ENH-010 | Low-contrast photo scans of TIN boxes unreadable | Extraction Coverage | EXTRACTION | P2 | S | added stretchContrast | Low-contrast crops failed OCR binarization, resulting in missed or blank reads. | Low-light / dim photo scans of the TIN box are now readable. | No contrast normalization was applied to the crop before OCR. -> added stretchContrast | Completed | 6/25/2026 | ) to stretch crop luminance to full black/white. (script.js, commit bc7ad01
ENH-011 | Single unconfirmed OCR reading of a TIN silently accepted | Extraction Confidence | EXTRACTION | P1 | S | raised threshold to bestCount >= 3 with tie-detection between whiteout/raw vote groups. | A reading with only 2 agreeing votes was accepted despite being wrong. | Fewer low-confidence OCR readings get accepted as fact. | Confidence threshold (bestCount >= 2) was too low, with no distinction between whiteout-pass and raw-pass votes. -> raised threshold to bestCount >= 3 with tie-detection between whiteout/raw vote groups. | Completed | 6/25/2026 | script.js, commit bc7ad01
ENH-012 | File upload rejects image scans despite bundled OCR support | Input Coverage | UPLOAD | P2 | S | extended accept to include jpeg/png/webp/heic/heif. | File picker/validation rejected image files, accepting only application/pdf. | Users can upload a phone photo/scan directly, not just a PDF. | accept="application/pdf" attribute excluded image MIME types. -> extended accept to include jpeg/png/webp/heic/heif. | Completed | 6/25/2026 | index.html, commit bc7ad01
ENH-013 | Extraction review warning easy to miss | UX / Accessibility | UI | P2 | S | replaced with a role="alert" banner with icon, moved above the fields. | Warning was plain, low-visibility hint text placed below the fields, easy to overlook. | Users are far less likely to miss that extraction should be double-checked. | No alert styling/role was applied to the warning text. -> replaced with a role="alert" banner with icon, moved above the fields. | Completed | 6/25/2026 | index.html, commit bc7ad01
ENH-014 | Tax ID field shows no dash formatting while typing | UX / Accessibility | UI | P3 | S | added formatTaxIdPartial for live dash formatting on every keystroke. | No formatting appeared until all 9 digits had been entered. | Tax ID field gives live visual feedback while typing instead of only at the end. | formatTaxId only formatted a complete 9-digit value. -> added formatTaxIdPartial for live dash formatting on every keystroke. | Completed | 8/26/2026 | script.js, uncommitted
ENH-015 | Recoverable length+1 OCR TIN readings discarded | Extraction Accuracy | EXTRACTION | P2 | M | added corroborated front/back trimming logic for length+1 readings. | Such readings were discarded entirely instead of being corrected. | Slightly-miscounted OCR readings are now recovered instead of thrown away. | No mechanism existed to trim a corroborated length+1 reading. -> added corroborated front/back trimming logic for length+1 readings. | Completed | 8/26/2026 | script.js, uncommitted

## Summary
Bugs vs. Enhancements — Summary
Category | Count
Bugs | 17
Enhancements | 15
Total | 32
Bugs by priority
Priority | Count
P0 | 2
P1 | 6
P2 | 7
P3 | 2
Enhancements by category
Category | Count
Extraction Accuracy | 7
Extraction Coverage | 3
UX / Accessibility | 2
Document Fidelity | 1
Extraction Confidence | 1
Input Coverage | 1